## Slide 1: NIS Implementation : SOP, Work Plan and Monitoring Framework
Md. Mahiuddin Khan
Additional Secretary (Reforms) Cabinet Division

## Slide 2: Implementation Cycle of NIS
SOP indicates, an implementation cycle of NIS that includes
  adequate planning
  proper implementation of the plan
  regular monitoring of the progress
  effective countermeasures to the issues identified by monitoring, and
  revision of the plan
Plan
Do
Action
Check

## Slide 3: Standaed Operating Procedure (SOP)
SOP is intended to provide a framework and clear guideline for the Ethics Committees for rendering the responsibilities as set out in their terms of reference
SOP explains necessary activities to be undertaken by the Ethics Committee
SOP is designed mainly as a guidebook for the Ethics Committee members and the integrity focal points
It is also useful for relevant officials of the Cabinet Division

## Slide 4: Key Contents of SOP
Roles and Responsibilities of Ethics Committee, Integrity Focal Point and National Integrity Implementation Unit (NIIU) of Cabinet Division
Operational Procedures
  Preparatory activities before the formulation of Ministry/Division/Institution specific NIS work-plan
  Formulation of ministry/division/organisation specific NIS work plan
  Monitor the implementation status of ministry/division specific NIS work plan
  Public Relations of NIS

## Slide 5: Formulation of NIS work plan
NIS itself provided some indicative work-plan for the selected institutions
Ministries/Divisions need to formulate their individual work-plan following the NIS messages and indications
In the work-plan, measurement indicators are set for each activity with time-frame

## Slide 6: Formulation of NIS work plan(2)
The indicators are used to measure progress of the plan
Responsible organization/unit/person for each activity also stated in NIS work plan
Ethics Committee is responsible for finalising the NIS work plan
Structure of the Work Plan is annexed with SOP

## Slide 7: Monitoring of NIS Implementation
Monitoring as a responsibility of the Ethics Committee
Monitoring as an APA requirement
Monitoring as a management tool

## Slide 8: Monitoring of NIS Implementation(2)
Purpose of monitoring
Proper implementation of the NIS work plan
Target of monitoring
Monitoring is conducted to measure progress of activities listed in the NIS work plan.
A gap between plan and actual progress needs to be checked.

## Slide 9: Monitoring of NIS Implementation(3)
Who is going to monitor
In general, monitoring is to be done by implementers themselves.
Integrity Focal Point is supposed to play a substantial role
Ethics Committee checks the progress and discusses countermeasures if there are factors obstructive to a plan
NIIU gathers monitoring results from ministries, divisions, and selected institutions and checks the overall progress of NIS.

## Slide 10: Monitoring of NIS Implementation(4)
Timing of monitoring
Every three month.
For the present NIS work plan Jan 2015 – Jun 2016, monitoring should be conducted in September and December 2015, March and June 2016.
How to monitor
Collecting information of progress on the NIS activities and fill out the monitoring template

## Slide 11: Flow of Activities
Gather necessary information
Compile the information and fill out the monitoring sheet/format
Submit the monitoring sheet/format to Ethics Committee
Monitoring by Ethics Committee
Submit the monitoring sheet/format to NIIU

## Slide 12: Flow of Activities (cont.)
Disseminate the monitoring results
Share experiences at Focal Point Workshop
Monitor the whole progress of NIS implementation
Report to Executive Committee for National Integrity Advisory Council

## Slide 13: Preparation for Monitoring NIS work-plan
Revise the NIS work-plan, if required
Disseminate the work-plan among stakeholders and concerned officials
Distribute responsibilities of implementation
Get the NIS work-plan approved by the Ethics Committee

## Slide 14: Way Forward
Implementation of NIS will be continued
Implementation of Existing work plan will be completed by June 2016
Ministries/Divisions need to formulate new work-plan for FY 2016-17 along with the monitoring framework
Ministries/Divisions will also need to prepare and submit quarterly monitoring report.

## Slide 15: Thank You